## Invoice
PRO-FORMA Invoice
Corporate Office: |  | GUT NO.14 B-10/4 E1 E2 E3 MIDC AREA, WALUJ AURANGABAD,CITY-WALUJ INDUSTR | GUT NO.14 B-10/4 E1 E2 E3 MIDC AREA, WALUJ AURANGABAD,CITY-WALUJ INDUSTR | Branch Office | M/s Sterlite Technologies Limited Neelkanth Commercial Co Op Soc Ltd Plot No 122/123, Office No 301-306, 3rd Floor,Sahar Road,Vile Parle (East), Mumbai - 400099
|  | GUT NO.14 B-10/4 E1 E2 E3 MIDC AREA, WALUJ AURANGABAD,CITY-WALUJ INDUSTR | GUT NO.14 B-10/4 E1 E2 E3 MIDC AREA, WALUJ AURANGABAD,CITY-WALUJ INDUSTR
Supplier's GSTIN |  | 27AAECS8719B1ZC | 27AAECS8719B1ZC
To, |  |  |  | Pro-Forma Invoice No | FTTH-MH-MP01-0116-1
| Reliance Projects & Property Management Services Limited | Comp, Reliance Projects & Property Management Services Limited | Comp, Reliance Projects & Property Management Services Limited | Pro-Forma Invoice Date | 2021-09-01
| Ghansoli,Navi Mumbai,5 TTC Industrial Area,Thane - Belapur Road | Ghansoli,Navi Mumbai, , , 5,TTC Industrial Area,Thane - Belapur Road | Ghansoli,Navi Mumbai, , , 5,TTC Industrial Area,Thane - Belapur Road | WO No. | P11/630108053
| Thane, Maharashtra, 400701 | Thane, Maharashtra, 400701 | Thane, Maharashtra, 400701 | WO Date | 2021-06-02
State Name |  | Maharashtra | Maharashtra | FSA Name | HOTEL SUPREME
|  |  |  | FSA ID | MUMB0116
GSTIN/Unique ID |  | 27AAJCR6636B1ZC | 27AAJCR6636B1ZC | Vendor Name | STERLITE TECHNOLOGIES LTD | STERLITE TECHNOLOGIES LTD
|  |  |  | Vendor Code | 0000378783 | 0000378783
PAN No Buyer |  | AAJCR6636B | AAJCR6636B | PAN NO. Vendor | AAECS8719B | AAECS8719B
|  |  |  | Service Period | 12-07-2021 TO 13-07-2021
|  |  |  | SAC Code | 998734 | 998734
|  |  |  | Place of supply of Service | Thane-Maharashtra | Thane-Maharashtra
S. No. | Service Description |  | Qty | UOM | Rate | Amount (Rs.)
1 | INSTALLATION OF FAT (WALL/POLE MOUNTED) |  | 2 | EA | 49 | 98
2 | INSTALLATION OF FDC |  | 1 | EA | 49 | 49
3 | INSTALLATION LEVEL 1 ( S1 ) SPLITTER |  | 1 | EA | 49 | 49
4 | INSTALLATION LEVEL 2 ( S2 ) SPLITTER |  | 2 | EA | 49 | 98
5 | BLOWING / PULLING-12 F |  | 169 | RMT | 7 | 1183
6 | BLOWING / PULLING-48 F |  | 55 | RMT | 10 | 550
7 | CHRG:SHALLOW TREN 40MM DUCT W/2 NOS |  | 5 | RMT | 160 | 800
8 | SPLICING,JOINTING & TERMINATION-48F |  | 21 | EA | 112 | 2352
9 | SPLICING & TERM OFC,FIXED COST/DAY |  | 0.375 | EA | 2425 | 909.375
10 | CHRG DRILLING OF HOLE 25MM DIA IN RCC |  | 3 | EA | 131 | 393
11 | S/FIXING PVC CONDUIT 40 MM |  | 85 | M | 111 | 9435
12 | SUP&LAY FLEX PVC CONDUIT DIA 40MM |  | 40 | EA | 116 | 4640
13 | P&F PVC JUNCTION BOX 40MM,4-WAY |  | 3 | EA | 30 | 90
14 | PREPARATION OF AS BUILT DRAWINGS DBP |  | 35 | RMT | 3 | 105
15 | A11102-SELF ADHESIVE LABELS |  | 6 | EA | 10 | 60
16 | CHRG;REINST,TRENCH,PCC-1:2:4,GRAVEL 20MM |  | 0.05 | Cu.M | 5335 | 266.75
|  |  |  | Total Supply Value (Basic) |  | 21078.125
|  |  |  | CGST @ 9% |  | 1897.0312
|  |  |  | SGST @ 9% |  | 1897.0312
|  |  |  | Total GST Payable |  | 3794.0625
|  |  |  | Total Bill Amount |  | 24872.1875
|  |  |  | Less- Advance |  | 0
|  |  |  | Net Payable Bill Amount |  | 24872.1875
|  |  |  | Round Off Net amount |  | 24873
Service Supply Amount in words: |  | Rupees Twenty Four Thousand Eight Hundred Seventy Three Only
GST Amount in words: |  | Rupees Three Thousand Seven Hundred Ninety Four and Paise Six Only
For ,STERLITE TECHNOLOGIES LTD.,
Authorised Signatory
Declaration:
a) Certified that all the particulars given above are true and correct.

## QCS
Quantity Certification Summary (QCS)
WO no : |  | P11/630108053
WO Date : |  | 2021-06-02 | Proforma Invoice No: | FTTH-MH-MP01-0116-1
Service Period : |  | 12-07-2021 TO 13-07-2021 | Building Nos | 2
FSA Name: |  | HOTEL SUPREME
FSA No : |  | MUMB0116
City |  | MP 01 (SOUTH)
Type of Work : |  | FTTX Work
This is to certify that following quantity pertaining to above mentioned Work Order of M/S. Sterlite Technologies Limited being invoiced as per details attached, has been completed.
S No. | Service Code | Item | UOM |  | Qty
| 3294022 | INSTALLATION OF FAT (WALL/POLE MOUNTED) | EA |  | 2
| 3259755 | INSTALLATION OF FDC | EA |  | 1
| 3293902 | INSTALLATION LEVEL 1 ( S1 ) SPLITTER | EA |  | 1
| 3293903 | INSTALLATION LEVEL 2 ( S2 ) SPLITTER | EA |  | 2
| 3294265 | BLOWING / PULLING-6 F | RMT |  | 0
| 3294710 | INSTALLATION 6F ADSS / FIG 8 CABLE | RMT |  | 0
| 3294264 | BLOWING / PULLING-12 F | RMT |  | 169
| 3294065 | INSTALLATION12F ADSS / FIG 8 CABLE | RMT |  | 0
| 3294262 | BLOWING / PULLING-48 F | RMT |  | 55
| 3294064 | INSTALLATION 48 F ADSS / FIG 8 CABLE | RMT |  | 0
| 3292713 | 96F BLOWING / PULLING ADSS | RMT |  | 0
| 3252599 | 96F BLOWING / PULLING | RMT |  | 0
| 3314515 | CHRG:SHALLOW TREN 40MM DUCT W/2 NOS | RMT |  | 5
| 3293883 | CHRG;SHALLOW TRENCH 40 OR 48MM 7WAY DUCT | RMT |  | 0
| 3252601 | SPLICING,JOINTING & TERMINATION-48F | EA |  | 21
| 3252602 | SPLICING,JOINTING & TERMINATION-96F | EA |  | 0
| 3300512 | SPLICING & TERM OFC,FIXED COST/DAY | EA |  | 0.375
| 3293884 | INSTALLATION OF THE POLE CLAMPS / ANCHOR PLATES | EA |  | 0
| 3294067 | INSTALLATION OF OTB (WALL/POLE MOUNTED) | EA |  | 0
| 3251233 | INSTALLATION OF FDMS/ FDP | EA |  | 0
| 3171149 | S/FIXING PVC CONDUIT 25 MM | M |  | 0
| 3318608 | S&I 25MM PVC CONDUIT USING SCAFFOLDING | M |  | 0
| 3206508 | SUP&LAY FLEX PVC CONDUIT DIA 25MM | M |  | 0
| 3318971 | S&I 25MM FLEXI PVC CONDUIT W/SCAFFOLDING | M |  | 0
| 3192918 | CHRG:S/F:PVC JUNCTION BOX 25MM,4-WAY | EA |  | 0
| 3126675 | DRILLING OF HOLES 25 MM | EA |  | 0
| 3318382 | CHRG DRILLING OF HOLE 25MM IN BRICK WALL | EA |  | 0
| 3318200 | CHRG DRILLING OF HOLE 25MM DIA IN RCC | EA |  | 3
| 3295960 | DISMANTLING OF 25MM CONDUIT | M |  | 0
| 3171151 | S/FIXING PVC CONDUIT 40 MM | M |  | 85
| 3318609 | S&I 40MM PVC CONDUIT USING SCAFFOLDING | M |  | 0
| 3206510 | SUP&LAY FLEX PVC CONDUIT DIA 40MM | EA |  | 40
| 3318972 | S&I 40MM FLEXI PVC CONDUIT W/SCAFFOLDING | M |  | 0
| 3319687 | P&F PVC JUNCTION BOX 40MM,4-WAY | EA |  | 3
| 3297469 | CHRG:DRILLING OF HOLE 40MM DIA IN RCC | EA |  | 0
| 3318381 | CHRG DRILLING OF HOLE 40MM IN BRICK WALL | EA |  | 0
| 3111341 | DISPOSAL OF WASTE MATERIALS DEBRIS ETC. | NOS |  | 0
| 3295194 | PREPARATION OF AS BUILT DRAWINGS SBP | EA |  | 0
| 3295195 | PREPARATION OF AS BUILT DRAWINGS DBP | RMT |  | 35
| 3157206 | DEBRIES DISPOSAL TRANSPORT | EA |  | 0
| 3295897 | CHRG: PRE EXECUTION BUILDING SURVEY | EA |  | 0
| 3295891 | MATERIAL STORAGE & SECONDARY TRNSPT | EA |  | 0
| 3098777 | A11102-SELF ADHESIVE LABELS | EA |  | 6
| 3324565 | LIASIONING FOR 96F BLOWING | M |  | 0
| 3297332 | DISMNTL/REMOVAL OF 40MM HDPE DUCT | M |  | 0
| 3293878 | CHRG;CLAMPING-1X40MM/1X7WAY MICRO DUCT | M |  | 0
| 3294239 | CHRG;REINST,TRENCH,PCC-1:2:4,GRAVEL 20MM | Cu.M |  | 0.05
| 3291784 | RSTRTN EXCVTD SURFACE-W/ PAVER BLOCK | M |  | 0
| 3290664 | CHRG F/RESTORATN OF SURF ;W/EXT TILES | M |  | 0
| 3342717 | CHRG COMPENSATION FOR COVID EXPENCE | EA |  | 0
Engineer |  | JC LEAD | FTTX LEAD |  | MPCM
STL |  | RJIO | RJIO |  | RJIO

## Abstact
ABSTRACT SHEET
Contractor Name : M/s. Sterlite Technologies Limited
WO Number : - |  |  | P11/630108053
Vendor Code |  |  | 378783
Proforma Invoice No :- |  |  | FTTH-MH-MP01-0116-1
OLT/FSA Name : - |  |  | HOTEL SUPREME
OLT/FSA ID : - |  |  | MUMB0116
Type Of Work : - |  |  | FTTX Work
Circle : - |  |  | MP 01 (SOUTH)
Work Done Period :- |  |  | 12-07-2021 TO 13-07-2021
S No. | SAC | JMS No | Service Code | Item | UOM | Rate | Total Quantity | Total Amount
| 998734 |  | 3294022 | INSTALLATION OF FAT (WALL/POLE MOUNTED) | EA | 49 | 2 | 98
| 998734 |  | 3259755 | INSTALLATION OF FDC | EA | 49 | 1 | 49
| 998734 |  | 3293902 | INSTALLATION LEVEL 1 ( S1 ) SPLITTER | EA | 49 | 1 | 49
| 998734 |  | 3293903 | INSTALLATION LEVEL 2 ( S2 ) SPLITTER | EA | 49 | 2 | 98
| 998734 |  | 3294265 | BLOWING / PULLING-6 F | RMT | 5 | 0 | 0
| 998734 |  | 3294710 | INSTALLATION 6F ADSS / FIG 8 CABLE | RMT | 19 | 0 | 0
| 998734 |  | 3294264 | BLOWING / PULLING-12 F | RMT | 7 | 169 | 1183
| 998734 |  | 3294065 | INSTALLATION12F ADSS / FIG 8 CABLE | RMT | 24 | 0 | 0
| 998734 |  | 3294262 | BLOWING / PULLING-48 F | RMT | 10 | 55 | 550
| 998734 |  | 3294064 | INSTALLATION 48 F ADSS / FIG 8 CABLE | RMT | 34 | 0 | 0
| 998734 |  | 3292713 | 96F BLOWING / PULLING ADSS | RMT | 40 | 0 | 0
| 998734 |  | 3252599 | 96F BLOWING / PULLING | RMT | 15 | 0 | 0
| 998734 |  | 3314515 | CHRG:SHALLOW TREN 40MM DUCT W/2 NOS | RMT | 160 | 5 | 800
| 998734 |  | 3293883 | CHRG;SHALLOW TRENCH 40 OR 48MM 7WAY DUCT | RMT | 160 | 0 | 0
| 998734 |  | 3252601 | SPLICING,JOINTING & TERMINATION-48F | EA | 112 | 21 | 2352
| 998734 |  | 3252602 | SPLICING,JOINTING & TERMINATION-96F | EA | 112 | 0 | 0
| 998734 |  | 3300512 | SPLICING & TERM OFC,FIXED COST/DAY | EA | 2425 | 0.375 | 909.375
| 998734 |  | 3293884 | INSTALLATION OF THE POLE CLAMPS / ANCHOR PLATES | EA | 97 | 0 | 0
| 998734 |  | 3294067 | INSTALLATION OF OTB (WALL/POLE MOUNTED) | EA | 49 | 0 | 0
| 998734 |  | 3251233 | INSTALLATION OF FDMS/ FDP | EA | 250 | 0 | 0
| 998734 |  | 3171149 | S/FIXING PVC CONDUIT 25 MM | M | 60 | 0 | 0
| 998734 |  | 3318608 | S&I 25MM PVC CONDUIT USING SCAFFOLDING | M | 133 | 0 | 0
| 998734 |  | 3206508 | SUP&LAY FLEX PVC CONDUIT DIA 25MM | M | 71 | 0 | 0
| 998734 |  | 3318971 | S&I 25MM FLEXI PVC CONDUIT W/SCAFFOLDING | M | 144 | 0 | 0
| 998734 |  | 3192918 | CHRG:S/F:PVC JUNCTION BOX 25MM,4-WAY | EA | 19 | 0 | 0
| 998734 |  | 3126675 | DRILLING OF HOLES 25 MM | EA | 43 | 0 | 0
| 998734 |  | 3318382 | CHRG DRILLING OF HOLE 25MM IN BRICK WALL | EA | 82 | 0 | 0
| 998734 |  | 3318200 | CHRG DRILLING OF HOLE 25MM DIA IN RCC | EA | 131 | 3 | 393
| 998734 |  | 3295960 | DISMANTLING OF 25MM CONDUIT | M | 10 | 0 | 0
| 998734 |  | 3171151 | S/FIXING PVC CONDUIT 40 MM | M | 111 | 85 | 9435
| 998734 |  | 3318609 | S&I 40MM PVC CONDUIT USING SCAFFOLDING | M | 188 | 0 | 0
| 998734 |  | 3206510 | SUP&LAY FLEX PVC CONDUIT DIA 40MM | EA | 116 | 40 | 4640
| 998734 |  | 3318972 | S&I 40MM FLEXI PVC CONDUIT W/SCAFFOLDING | M | 194 | 0 | 0
| 998734 |  | 3319687 | P&F PVC JUNCTION BOX 40MM,4-WAY | EA | 30 | 3 | 90
| 998734 |  | 3297469 | CHRG:DRILLING OF HOLE 40MM DIA IN RCC | EA | 165 | 0 | 0
| 998734 |  | 3318381 | CHRG DRILLING OF HOLE 40MM IN BRICK WALL | EA | 131 | 0 | 0
| 998734 |  | 3111341 | DISPOSAL OF WASTE MATERIALS DEBRIS ETC. | NOS | 679 | 0 | 0
| 998734 |  | 3295194 | PREPARATION OF AS BUILT DRAWINGS SBP | EA | 194 | 0 | 0
| 998734 |  | 3295195 | PREPARATION OF AS BUILT DRAWINGS DBP | RMT | 3 | 35 | 105
| 998734 |  | 3157206 | DEBRIES DISPOSAL TRANSPORT | EA | 291 | 0 | 0
| 998734 |  | 3295897 | CHRG: PRE EXECUTION BUILDING SURVEY | EA | 290 | 0 | 0
| 998734 |  | 3295891 | MATERIAL STORAGE & SECONDARY TRNSPT | EA | 485 | 0 | 0
| 998734 |  | 3098777 | A11102-SELF ADHESIVE LABELS | EA | 10 | 6 | 60
| 998734 |  | 3324565 | LIASIONING FOR 96F BLOWING | M | 3 | 0 | 0
| 998734 |  | 3297332 | DISMNTL/REMOVAL OF 40MM HDPE DUCT | M | 5 | 0 | 0
| 998734 |  | 3293878 | CHRG;CLAMPING-1X40MM/1X7WAY MICRO DUCT | M | 49 | 0 | 0
| 998734 |  | 3294239 | CHRG;REINST,TRENCH,PCC-1:2:4,GRAVEL 20MM | Cu.M | 5335 | 0.05 | 266.75
| 998734 |  | 3291784 | RSTRTN EXCVTD SURFACE-W/ PAVER BLOCK | M | 631 | 0 | 0
| 998734 |  | 3290664 | CHRG F/RESTORATN OF SURF ;W/EXT TILES | M | 286 | 0 | 0
| 998734 |  | 3342717 | CHRG COMPENSATION FOR COVID EXPENCE | EA | 1800 | 0 | 0
Total Amount Of Work Done / Invoice | [7 empty] | 21078.125
Certified By:-
FTTX JC LEAD |  |  | MP FTTX LEAD | MPCM | State Head
SIGNATURE

## Bldg Annexture
BUILDING ANNEXURE
Vendor Name :- Sterlite Technologies Limited |  |  |  |  | Type Of Work :- Services & Supply.
OLT/FSA Name : - |  | HOTEL SUPREME |  |  | WO Number : - | P11/630108053
OLT/FSA ID : - |  | MUMB0116
Area :- | MP 01 (SOUTH) |  |  |  | WO Date : - | 2021-06-02
Work done Period |  | 12-07-2021 TO 13-07-2021 |  |  | Proforma Invoice No :- | FTTH-MH-MP01-0116-1
S No. | Bldg Name | BUILDING_RJID | ITP Date | Work Start Date | Work Completion Date | Remarks
1 | Colaba Mun Sec School | MUMBBD0248348 | 2021-07-13 | 2021-07-12 | 2021-07-12 | HOTO done | 4173-027/028
2 | BMC Primary School | MUMBBD0212907 | 2021-07-13 | 2021-07-12 | 2021-07-12 | HOTO done | 4173-025/026
| TOTAL NO OF BLDG | 2
Certified By:-
FTTX JC LEAD |  | MP FTTX LEAD |  | MPCM |  | State Construction Head
Signature

## WCC
RELIANCE PROJECTS & PROPERTY MANAGEMENT SERVICES LIMITED
WORK COMPLETION CERTIFICATE
Activity : | FTTH service | FSA NO : | MUMB0116
WO Date: | 2021-06-02 | BUILDING NOs: | 2
Type of Work: | FTTX
City : | MP 01 (SOUTH)
This is to certify that the work has been completed by M/S Sterlite Technologies Limited in South Mumbai (HOTEL SUPREME MUMB0116) area with reference to the activity mentioned above of the sites attached herewith as per Annexure " A". The work done in accordance with scope of work / work order.
| Building Name & ID | As per Building Annexure attached
| No. of Sites Completed | 1
| Work Order No. | P11/630108053
| WO Date | 2021-06-02
| Work Start Period | 12-07-2021
| Work End Period | 12-07-2021
Engineer | JC LEAD | FTTX LEAD | MPCM
STL | RJIO | RJIO | RJIO

## JMR
Joint Measurment Sheet
Vendor Name : M/s. Sterlite Technologies Limited
WO Number : - |  | P11/630108053
Vendor Code : |  | 378783
Proforma Invoice No :- |  | FTTH-MH-MP01-0116-1
OLT/FSA Name : - |  | HOTEL SUPREME
OLT/FSA ID : - |  | MUMB0116
Work Done Period :- |  | 12-07-2021 TO 13-07-2021
Circle : |  | MP 01 (SOUTH)
NO OF SITES |  | 1
S No. | Service Code | Item | Bldg Name & Add | Colaba Mun Sec School |  | BMC Primary School |  |  | Total Quantity | Remarks
|  |  | Bldg ID> | MUMBBD0248348 |  | MUMBBD0212907
|  |  | MB Sheet No. | 4173-027 | 4173-028 | 4173-025 | 4173-026
|  |  | UOM | Actual Qty | Actual Qty | Actual Qty | Actual Qty | Actual Qty
| 3294022 | INSTALLATION OF FAT (WALL/POLE MOUNTED) | EA | 1 |  | 1 |  |  | 2
| 3259755 | INSTALLATION OF FDC | EA |  |  | 1 |  |  | 1
| 3293902 | INSTALLATION LEVEL 1 ( S1 ) SPLITTER | EA |  |  | 1 |  |  | 1
| 3293903 | INSTALLATION LEVEL 2 ( S2 ) SPLITTER | EA | 1 |  | 1 |  |  | 2
| 3294265 | BLOWING / PULLING-6 F | RMT | [5 empty] | 0
| 3294710 | INSTALLATION 6F ADSS / FIG 8 CABLE | RMT | [5 empty] | 0
| 3294264 | BLOWING / PULLING-12 F | RMT | 160 |  | 9 |  |  | 169
| 3294065 | INSTALLATION12F ADSS / FIG 8 CABLE | RMT | [5 empty] | 0
| 3294262 | BLOWING / PULLING-48 F | RMT |  |  | 55 |  |  | 55
| 3294064 | INSTALLATION 48 F ADSS / FIG 8 CABLE | RMT | [5 empty] | 0
| 3292713 | 96F BLOWING / PULLING ADSS | RMT | [5 empty] | 0
| 3252599 | 96F BLOWING / PULLING | RMT | [5 empty] | 0
| 3314515 | CHRG:SHALLOW TREN 40MM DUCT W/2 NOS | RMT |  | 5 |  |  |  | 5
| 3293883 | CHRG;SHALLOW TRENCH 40 OR 48MM 7WAY DUCT | RMT | [5 empty] | 0
| 3252601 | SPLICING,JOINTING & TERMINATION-48F | EA | 3 |  |  | 18 |  | 21
| 3252602 | SPLICING,JOINTING & TERMINATION-96F | EA | [5 empty] | 0
| 3300512 | SPLICING & TERM OFC,FIXED COST/DAY | EA | 0.125 |  |  | 0.25 |  | 0.375
| 3293884 | INSTALLATION OF THE POLE CLAMPS / ANCHOR PLATES | EA | [5 empty] | 0
| 3294067 | INSTALLATION OF OTB (WALL/POLE MOUNTED) | EA | [5 empty] | 0
| 3251233 | INSTALLATION OF FDMS/ FDP | EA | [5 empty] | 0
| 3171149 | S/FIXING PVC CONDUIT 25 MM | M | [5 empty] | 0
| 3318608 | S&I 25MM PVC CONDUIT USING SCAFFOLDING | M | [5 empty] | 0
| 3206508 | SUP&LAY FLEX PVC CONDUIT DIA 25MM | M | [5 empty] | 0
| 3318971 | S&I 25MM FLEXI PVC CONDUIT W/SCAFFOLDING | M | [5 empty] | 0
| 3192918 | CHRG:S/F:PVC JUNCTION BOX 25MM,4-WAY | EA | [5 empty] | 0
| 3126675 | DRILLING OF HOLES 25 MM | EA | [5 empty] | 0
| 3318382 | CHRG DRILLING OF HOLE 25MM IN BRICK WALL | EA | [5 empty] | 0
| 3318200 | CHRG DRILLING OF HOLE 25MM DIA IN RCC | EA |  |  |  | 3 |  | 3
| 3295960 | DISMANTLING OF 25MM CONDUIT | M | [5 empty] | 0
| 3171151 | S/FIXING PVC CONDUIT 40 MM | M | 55 |  | 30 |  |  | 85
| 3318609 | S&I 40MM PVC CONDUIT USING SCAFFOLDING | M | [5 empty] | 0
| 3206510 | SUP&LAY FLEX PVC CONDUIT DIA 40MM | EA | 20 |  | 20 |  |  | 40
| 3318972 | S&I 40MM FLEXI PVC CONDUIT W/SCAFFOLDING | M | [5 empty] | 0
| 3319687 | P&F PVC JUNCTION BOX 40MM,4-WAY | EA |  |  | 3 |  |  | 3
| 3297469 | CHRG:DRILLING OF HOLE 40MM DIA IN RCC | EA | [5 empty] | 0
| 3318381 | CHRG DRILLING OF HOLE 40MM IN BRICK WALL | EA | [5 empty] | 0
| 3111341 | DISPOSAL OF WASTE MATERIALS DEBRIS ETC. | NOS | [5 empty] | 0
| 3295194 | PREPARATION OF AS BUILT DRAWINGS SBP | EA | [5 empty] | 0
| 3295195 | PREPARATION OF AS BUILT DRAWINGS DBP | RMT |  |  |  | 35 |  | 35
| 3157206 | DEBRIES DISPOSAL TRANSPORT | EA | [5 empty] | 0
| 3295897 | CHRG: PRE EXECUTION BUILDING SURVEY | EA | [5 empty] | 0
| 3295891 | MATERIAL STORAGE & SECONDARY TRNSPT | EA | [5 empty] | 0
| 3098777 | A11102-SELF ADHESIVE LABELS | EA | 2 |  |  | 4 |  | 6
| 3324565 | LIASIONING FOR 96F BLOWING | M | [5 empty] | 0
| 3297332 | DISMNTL/REMOVAL OF 40MM HDPE DUCT | M | [5 empty] | 0
| 3293878 | CHRG;CLAMPING-1X40MM/1X7WAY MICRO DUCT | M | [5 empty] | 0
| 3294239 | CHRG;REINST,TRENCH,PCC-1:2:4,GRAVEL 20MM | Cu.M |  | 0.05 |  |  |  | 0.05
| 3291784 | RSTRTN EXCVTD SURFACE-W/ PAVER BLOCK | M | [5 empty] | 0
| 3290664 | CHRG F/RESTORATN OF SURF ;W/EXT TILES | M | [5 empty] | 0
| 3342717 | CHRG COMPENSATION FOR COVID EXPENCE | EA | [5 empty] | 0
STL Engineer |  | RJIO JC LEAD | FTTX LEAD |  | MPCM

## Mat Con
Material Consumption Statement-Sitewise.
Vendor Name : |  | M/s. Sterlite Technologies Limited
Work Order no |  | P11/630108053
Vendor Code : |  | 378783
Proforma Invoice No :- |  | FTTH-MH-MP01-0116-1
OLT/FSA Name : - |  | HOTEL SUPREME
OLT/FSA ID : - |  | MUMB0116
Work Done Period :- |  | 12-07-2021 TO 13-07-2021
Circle : |  | MP 01 (SOUTH)
SL No. | Matcode | Material Description | Bldg Name & Add | Colaba Mun Sec School |  | BMC Primary School |  | 0 | TOTAL
|  |  | Bldg ID > | MUMBBD0248348 |  | MUMBBD0212907 |  | 0
|  |  | MB Sheet No. | 4173-027 | 4173-028 | 4173-025 | 4173-026 | 0
| 2001980257 | OFC ARM 3LT X 2F HDPE 6F SM FRP F/ENTP | RMT | [5 empty] | 0
| 2001614563 | OFC ADSS G652D 2F/T 6F SM | RMT | [5 empty] | 0
| 2001896635 | OFC LASHED AERIAL 6F SM G652D | RMT | [5 empty] | 0
| 2001642697 | OFC N-ARM 6F RISER LSZH SM FRP | RMT | [5 empty] | 0
| 2001599464 | OFC N-ARM MICRO HDPE 6F SM FRP | RMT | [5 empty] | 0
| 2001980254 | OFC ARM 6LT X 2F HDPE 12F SM FRP F/ENTP | RMT | 160 |  |  |  |  | 160
| 2001614562 | OFC ADSS G652D 2F/T 12F SM | RMT | [5 empty] | 0
| 2001896633 | OFC LASHED AERIAL 12F SM G652D | RMT | [5 empty] | 0
| 2001599466 | OFC N-ARM MICRO HDPE 12F SM FRP | RMT | [5 empty] | 0
| 2001642663 | OFC N-ARM 12F RISER LSZH SM N/A | RMT |  |  | 9 |  |  | 9
| 2001979500 | OFC ARM 8LT X 6F HDPE 48F SM FRP F/ENTP | RMT |  |  | 55 |  |  | 55
| 2001979498 | OFC ARM 8LT X 6F HDPE 48F SM FRP F/FTTX | RMT | [5 empty] | 0
| 2001614561 | OFC ADSS G652D 6F/T 48F SM | RMT | [5 empty] | 0
| 2001896599 | OFC LASHED AERIAL 48F SM G652D | RMT | [5 empty] | 0
| 2001599465 | OFC N-ARM MICRO ORANGE 48F SM FRP | RMT | [5 empty] | 0
| 2001980762 | OFC ARM 8LT X 12F HDPE 96F SM FRP F/ENTP | RMT | [5 empty] | 0
| 2001614560 | OFC ADSS G652D12F/T 96F SM | RMT | [5 empty] | 0
| 2001896619 | OFC LASHED AERIAL 96F SM G652D | RMT | [5 empty] | 0
| 2001791604 | OFC N-ARM MICRO PURPLE 96F SM FRP | RMT | [5 empty] | 0
| 2001957481 | DUCT,HDPE,GREY,40 ODX3.5MM T,WHITE STRPS | RMT |  | 5 |  |  |  | 5
| 2001512960 | DUCT,HDPE,RED,LUB,40 OD X 3.5MM | RMT | [5 empty] | 0
| 2001899648 | ANCHOR PLATE,WALL,CORNER;SWL-1.04T | EA | [5 empty] | 0
| 2001898285 | HELIX,PROTECTIVE,F/12.5MM ADSS OFC | EA | [5 empty] | 0
| 2001898288 | HELIX,TERMINATING,F/11.5MM ADSS OFC | EA | [5 empty] | 0
| 2001898362 | HELIX,TERMINATING,F/12.5MM ADSS OFC | EA | [5 empty] | 0
| 2001899702 | CELVIS THIMBLE,0.9T;100 MTRS,100 KM/HR | EA | [5 empty] | 0
| 2001899704 | THIMBLE,0.5T; 100 MTRS SPAN;100 KM/HR | EA | [5 empty] | 0
| 2001899706 | TWISTED LINK,1.25T, F/11.5MM ADSS OFC | EA | [5 empty] | 0
| 2001899708 | TURN BUCKLE;0.75T;100 MTRS SPAN;100KM/HR | EA | [5 empty] | 0
| 2001899709 | D-SHACKLE 0.75T; 100 MTRS SPAN, 100 KM/H | EA | [5 empty] | 0
| 2001899711 | ANCHOR FASTENER; M10 F/ANCHOR PLATE | EA | [5 empty] | 0
| 2001899714 | ANCHOR FASTENER; M12 F/ANCHOR PLATE | EA | [5 empty] | 0
| 2001899624 | ANCHOR,PLATE,WALL;SQUARE;SWL-1.04T | EA | [5 empty] | 0
| 2001899712 | CABLE,LASH,SS(11.5/12.5MM)CLIP F/4MM WRE | EA | [5 empty] | 0
| 2001701769 | RPE STL WIRE GAL 6 X7 FC 4.0MM RH | EA | [5 empty] | 0
| 2001899713 | BRACKET,CABLE STORAGE;WALL;F/ADSS OFC | EA | [5 empty] | 0
| 2001994563 | FLEXIBLE INNER DUCT,2 WAY,W/PULL ROPES | RMT | [5 empty] | 0
| 2001994568 | FLEXIBLE INNER DUCT,3 WAY,W/PULL ROPES | RMT | [5 empty] | 0
| 2001899707 | TWISTED LINK,1.25T; F/12.5MM ADSS OFC | EA | [5 empty] | 0
| 2001899710 | ANCHOR,PLATE,WALL,TRIANGULAR;SWL-1.04T | EA | [5 empty] | 0
| 2001903837 | BRACKET,CABLE STORAGE,POLE,F/ADSS OFC | EA | [5 empty] | 0
| 2001899563 | HELICAL GRIP;SWL-0.9T; F/4MM MSG WIRE | EA | [5 empty] | 0
| 2001898284 | HELIX,PROTECTIVE,F/11.5MM ADSS OFC | EA | [5 empty] | 0
| 2001898287 | HELIX,SUSPENSION,F/11.5MM ADSS OFC | EA | [5 empty] | 0
| 2001898286 | HELIX,SUSPENSION,F/12.5MM ADSS OFC | EA | [5 empty] | 0
| 2002053189 | CELVIS THIMBLE ; SWL 0.75T-ERT / FTTX | EA | [5 empty] | 0
| 2002053193 | PROTECTIVE HELIX ; 11.5MM OFC-ERT - FTTX | EA | [5 empty] | 0
| 2002053200 | D-SHACKLE 0.75T-ERT / FTTX | EA | [5 empty] | 0
| 2002053335 | TURN BUCLE ; SWL 0.75T-ERT / FTTX | EA | [5 empty] | 0
| 2002053196 | THIMBLE ; SWL 0.75T-ERT/FTTX | EA | [5 empty] | 0
| 2001698824 | TERMINATING HELIX FOR 12.5MM OFC-VK | EA | [5 empty] | 0
| 2002114405 | TERMINATING HELIX FOR 12.5MM OFC-TSH/FTTX | EA | [5 empty] | 0
| 2002114409 | CELVIS THIMBLE ; SWL 0.75T-TSH / FTTX | EA | [5 empty] | 0
| 2002114411 | TURN BUCLE ; SWL 0.75T-TSH / FTTX | EA | [5 empty] | 0
| 2002114412 | D-SHACKLE 0.75T-TSH / FTTX | EA | [5 empty] | 0
| 2001901417 | FDP,FTTX,1X96F,LCAPC INT PATCH CORD MANA | EA | [5 empty] | 0
| 2001901152 | FDP,FTTX,1X48F,LCAPC INT PATCH CORD MANA | EA | [5 empty] | 0
| 2001684298 | FDP FTTX ODC 1X96 F LCAPC DUPLEX | EA | [5 empty] | 0
| 2001684299 | FDP FTTX ODC 1X48 F LCAPC DUPLEX | EA | [5 empty] | 0
| 2001980237 | FDP,12T,LT, FOR 12F ARM OFC,TYPE-111 | EA | [5 empty] | 0
| 2001980262 | FDP,6T,LT, FOR 6F ARM OFC,TYPE-112 | EA | [5 empty] | 0
| 2001684296 | FDP FTXMAST LCSPC DU RYCHM FDMS001 1X96F | EA | [5 empty] | 0
| 2001629660 | FDC- FIBER DISTRIBUTN CABINET-FTTX | EA |  |  | 1 |  |  | 1
| 2001631008 | FAT-FIBER ACCESS TERMINAL-FTTX | EA | 1 |  | 1 |  |  | 2
| 2001582563 | FIBRE ACESS TERMINAL.(FAT),48F | EA | [5 empty] | 0
| 2001629657 | SPLITTER PLC-2:8 900BARE END_FTTX | EA | [5 empty] | 0
| 2001603054 | SPLITTER,PLC,TYPE:2X8,U1/19"RACK MOUNT | EA | [5 empty] | 0
| 2001976074 | SPLITTER,PLC,2:8 W/CONNECTOR,LC-APC | EA | [5 empty] | 0
| 2001976400 | FDP,SPLITTER BANK,F/4NOS 2:8 SPLITTER,1U | EA | [5 empty] | 0
| 2002064531 | SPLITTER 2X8,PLC-208-LC/APC-S | EA |  |  | 1 |  |  | 1
| 2001753065 | SPLITTER PLC-1:8 BARE TYPE_FTTX | EA | [5 empty] | 0
| 2001629658 | SPLITTER PLC-1:8 CASSETTE TYPE_FTTX | EA | 1 |  | 1 |  |  | 2
| 2001570697 | SPLITTER 1:8,SC/APC,19"RACK MOUNTED | EA | [5 empty] | 0
| 2002064368 | SPLITTER,1X8,PLC,MM: PLC-108-SC/APC-LGX-B | EA | [5 empty] | 0
| 2001629661 | JOINT CLOSURE-96F-FTTX | EA |  |  | 2 |  |  | 2
| 2001987936 | JC,FLAT,96 SPLICE,4 SPLITTER,ARM,LT OFC | EA | [5 empty] | 0
| 2001980575 | CLOSURE,JOINT,OFC,96F(INDIVIDUAL) F/ENTP | EA | [5 empty] | 0
| 2001628886 | OPTICAL/OUTDOOR TEMINAL BOX - OTB - FTTX | EA | [5 empty] | 0
| 2001774089 | MANAGER PATCH CORD 19'' FDP | EA | [5 empty] | 0
| 2001774108 | PATCH CORD STORAGE_1U | EA | [5 empty] | 0
| 2001602356 | CABLE MANAGER,HORIZONTAL,19",RACK MOUNT | EA | [5 empty] | 0
| 2001734751 | PIGTAIL,SC/APC,G.657A,1.5M | EA | [5 empty] | 0
| 2001632492 | ACCESS CHAMBER,HD-20;750X400X500MM | EA | [5 empty] | 0
| 5000014404 | MANHOLE,900X600X800,BOX,MODU,FRP,HD20 | EA | [5 empty] | 0
| 5000012529 | MANHOLE,FRP,W/COVER,400X400X500 MM-MD-10 | EA | [5 empty] | 0
| 2001648168 | TOBY BOX ,FLOOR MOUNT F/ FTTH | EA | [5 empty] | 0
| 2001648166 | TOBY BOX ,WALL MOUNT F/ FTTH | EA | [5 empty] | 0
| 2001997012 | FTTH-EARTHING KIT FOR FAT-TE | EA | [5 empty] | 0
| 2001997013 | FTTH-EARTHING KIT,FOR OTB-TE | EA | [5 empty] | 0
| 2001997014 | FTTH-EARTHING KIT F/FDC-TE,PN:EM0096-000 | EA | [5 empty] | 0
| 2001997015 | FTTH-EARTHING KIT,F/JOINT CLOSURE-TE | EA | [5 empty] | 0
| 2001719927 | POLE CIRCULAR OD114,THK 5.4MM,HT 7.5M | EA | [5 empty] | 0
| 2002092946 | OFC ADSS G652D 6F/T 48F SM,TYPE-9-IGFY | RMT | [5 empty] | 0
| 2002092918 | OFC ADSS G652D 2F/T 12F SM, TYPE-9-IGFY | RMT | [5 empty] | 0
| 2001548397 | CLOSURE, JOINT, OFC, 48F(6LT X 8F) | EA | [5 empty] | 0
STL Engineer |  | RJIO JC LEAD | FTTX LEAD |  | MPCM