## Invoice
PRO-FORMA Invoice
Corporate Office: | GUT NO.14 B-10/4 E1 E2 E3 MIDC AREA, WALUJ AURANGABAD,CITY-WALUJ INDUSTR |  |  | Branch Office | M/s Sterlite Technologies Limited Neelkanth Commercial Co Op Soc Ltd Plot No 122/123, Office No 301-306, 3rd Floor,Sahar Road,Vile Parle (East), Mumbai - 400099
Supplier's GSTIN |  | 27AAECS8719B1ZC | 27AAECS8719B1ZC
To, |  |  |  | Pro-Forma Invoice No | TNDMNETMP01-3
| Reliance Projects & Property Management Services Limited | Comp, Reliance Projects & Property Management Services Limited | Comp, Reliance Projects & Property Management Services Limited | Pro-Forma Invoice Date | 2021-12-04
| Ghansoli,Navi Mumbai,5 TTC Industrial Area,Thane - Belapur Road | Ghansoli,Navi Mumbai, , , 5,TTC Industrial Area,Thane - Belapur Road | Ghansoli,Navi Mumbai, , , 5,TTC Industrial Area,Thane - Belapur Road | WO No. | P11/630098168
| Thane, Maharashtra, 400701 | Thane, Maharashtra, 400701 | Thane, Maharashtra, 400701 | WO Date | 2021-08-09
State Name |  | Maharashtra | Maharashtra | LINK/FSA Name | MUMB0309
|  |  |  | LINK/FSA ID | KONARK
GSTIN/Unique ID |  | 27AAJCR6636B1ZC | 27AAJCR6636B1ZC | Vendor Name | STERLITE TECHNOLOGIES LTD | STERLITE TECHNOLOGIES LTD
|  |  |  | Vendor Code | 0000378783 | 0000378783
PAN No Buyer |  | AAJCR6636B | AAJCR6636B | PAN NO. Vendor | AAECS8719B | AAECS8719B
|  |  |  | Service Period | 12-02-2021 To 12-02-2021
|  |  |  | SAC Code | 998734 | 998734
|  |  |  | Place of supply of Service | Thane-Maharashtra | Thane-Maharashtra
S. No. | Service Description | Qty | UOM | Rate | % Milestone (C) | Amount (Rs.)
1 | 3343442-LAY OFC-4 DUCTS-OT-T1-CORE/AGG-96F/288F | 89 | RMT | 535 | 80% | 38092
2 | 3242510-PROVIDING OF END PLUG | 28 | EA | 44 | 80% | 985.6
3 | 3319693-S&I COUPLER,F/40MM HDPE DUCT | 13 | EA | 120 | 80% | 1248
4 | 3318198-S&I DBL WALL CORRUGATED DUCT-110NB | 96 | RMT | 116 | 80% | 8908.8
5 | 3143695-PROV &LAYING PCC M:15-ALL THK | 8.01 | CuM | 5335 | 80% | 34186.68
6 | 3253157-S& I OF MANHOLE (BLOCK MH 600*900) | 1 | EA | 15423 | 80% | 12338.4
7 | 3235737-CHARGS INST FRP MH/HH - 900x600 | 1 | EA | 4365 | 80% | 3492
|  |  |  | Total Supply Value (Basic) |  | 99251.48
|  |  |  | CGST @ 9% |  | 8932.6332
|  |  |  | SGST @ 9% |  | 8932.6332
|  |  |  | Total GST Payable |  | 17865.2664
|  |  |  | Total Bill Amount |  | 117116.7464
|  |  |  | Less- Advance |  | 0
|  |  |  | Net Payable Bill Amount |  | 117116.7464
|  |  |  | Round Off Net amount |  | 117117
Service Supply Amount in words: | Rupees One Lakh Seventeen Thousand One Hundred Seventeen Only
GST Amount in words: | Rupees Seventeen Thousand Eight Hundred Sixty Five and Paise Twenty Six Only
For ,STERLITE TECHNOLOGIES LTD.,
Authorised Signatory
Declaration:
a) Certified that all the particulars given above are true and correct.

## QCS
Quantity Certification Summary (QCS)
WO no : |  |  | P11/630098168
WO Date : |  |  | 2021-08-09 | PROFORMA INVOICE NO. | TNDMNETMP01-3
Service Period : |  |  | 12-02-2021 To 12-02-2021
AREA |  |  | MP 01 (MCGM)
Type of Work : |  |  | MAHNET T & D WORK
This is to certify that following quantity pertaining to above mentioned Work Order of M/S. Sterlite Technologies Limited being invoiced as per details attached, has been completed.
S No. | FSA Id | Service Code | Description/ Activity-MUMB0309 (KONARK) | UOM | Qty | Milestone | JMS NO.
1 | MUMB0309 | 3343442 | LAY OFC-4 DUCTS-OT-T1-CORE/AGG-96F/288F | RMT | 89 | 80% |  | 535 | 38092 | Amendment Req
2 | MUMB0309 | 3242510 | PROVIDING OF END PLUG | EA | 28 | 80% |  | 44 | 985.6 | Amendment Req
3 | MUMB0309 | 3319693 | S&I COUPLER,F/40MM HDPE DUCT | EA | 13 | 80% |  | 120 | 1248 | Amendment Req
4 | MUMB0309 | 3318198 | S&I DBL WALL CORRUGATED DUCT-110NB | RMT | 96 | 80% |  | 116 | 8908.8 | Amendment Req
5 | MUMB0309 | 3143695 | PROV &LAYING PCC M:15-ALL THK | CuM | 8.01 | 80% |  | 5335 | 34186.68 | Amendment Req
6 | MUMB0309 | 3253157 | S& I OF MANHOLE (BLOCK MH 600*900) | EA | 1 | 80% |  | 15423 | 12338.4 | Amendment Req
7 | MUMB0309 | 3235737 | CHARGS INST FRP MH/HH - 900x600 | EA | 1 | 80% |  | 4365 | 3492 | Amendment Req
Certified By:-
T&D JC LEAD |  |  | MP T&D LEAD |  | MPCM
SIGNATURE |  |  | SIGNATURE |  | SIGNATURE
ROW Head |  |  | State Construction Head
SIGNATURE |  |  | SIGNATURE

## MTSUMMARY (hidden)
STERLITE TECHNOLOGIES LIMITED
RJIL 4G INTRA-CITY OFC NETWORK SITE, MUMBAI
| AREA :- | MP 03 (MCGM)
| WO NUMBER : - | 630125209
WO DATE : -
| PROFORMA INVOICE NO :- | TND-MNET-MP03-2
WORK PERIOD :-
| MEASUREMENT ABSTRACT SHEET |  |  |  |  | Trenching- Form No.54 |  |  | Ductlaying- Form No. 55 |  |  | Backfilling- Form-56
Sr No. | Location of Work |  | Chainage (every 20m) |  | No. Of Duct | ITP Date | Ref. ITP No. | Actual Length in Meters | ITP Date | Ref. ITP No. | Actual Length in Meters | ITP Date | Ref. ITP No. | Actual Length in Meters | Strata |  | Sealant | LINK NO. | Permit No
| From | To | From | To | [10 empty] | Normal soil | Hard Rock | In Bags
(03 Duct) | [19 empty] | Sealant | O | G | V | R
1 |  |  |  |  | 03 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [5 empty] | 0 |  | 150 | 150 | 150
2 |  |  |  |  | 03 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [5 empty] | 0 |  | 102 | 102 | 102
3 |  |  |  |  | 03 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [5 empty] | 0 |  | 115 | 115 | 115
4 |  |  |  |  | 03 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [5 empty] | 0 |  | 72 | 72 | 72
5 |  |  |  |  | 03 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [5 empty] | 0 |  | 60 | 60 | 60
6 |  |  |  |  | 03 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [5 empty] | 0 |  | 70 | 70 | 70
7 |  |  |  |  | 03 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [5 empty] | 0 |  | 140 | 140 | 140
TOTAL LENGTH OF WORKDONE (03 Duct) | [7 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 709 | 709 | 709
4 |  |  |  |  | 06 |  |  | 0 | 0 |  | 0 | 0 |  | 0 | [5 empty] | 0
0
TOTAL LENGTH OF WORKDONE (06 Duct) | [7 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
Certified By
| T&D JC LEAD |  | MP T&D LEAD | [6 empty] | MPCM |  |  |  | State Construction Head
Formulas:
Ductlaying- Form No. 55 = [Trenching- Form No.54]
Backfilling- Form-56 = +[Ductlaying- Form No. 55]

## OT SUMMARY
SUMMARY OPEN-TRENCHING WORK
Invoice No:- |  |  | TNDMNETMP01-3
WO No:- |  |  | P11/630098168
Work Period:- |  |  | 12-02-2021 To 12-02-2021
Area:- |  |  | MP 01 (MCGM)
S.NO | LOCATION | Service Code | ITP NO | DATE | CHAINAGE-OPEN TRECNH |  | ACTUAL LENGTH | Depth of Trench | NO OF Ducts | End Caps - 3319691 | DWC COUPLER | DWC Pipe 110mm | PCC | REMARKS
[5 empty] | FROM | TO
A | KONARK |  | MUMB0309 | P NO.783247281 | [10 empty] | O | G | V | R
1 | Near Konark Gate To Worli Naka |  | 4315-035 | 2021-02-12 | 0 | 89 | 89 | 0.65 | 4 | 16 | [5 empty] | 0
2 | Near Konark OLT Bldg Gate To Worli Naka |  | 4315-036 | 2021-02-12 | 0 |  | 0 |  |  |  | 13 | 96 | 8.01 |  |  | 0
[7 empty] | 89 |  |  | 16 | 13 | 96 | 8.01 |  | 0 | 0 | 0 | 0
Certified By:-
| Site Engineer (STL) |  | FTTX JC |  |  | FTTX JC LEAD |  |  |  |  | MPCM
| SIGNATURE |  | SIGNATURE |  |  | SIGNATURE |  |  |  |  | SIGNATURE

## Manhole
STERLITE TECHNOLOGIES LIMITED
AREA :- |  | MP 01 (MCGM)
WO NUMBER : - |  | P11/630098168
WO DATE : - |  | 2021-08-09
PROFORMA INVOICE NO :- |  | TNDMNETMP01-3
WORK PERIOD : |  | 12-02-2021 To 12-02-2021
MANHOLE-ITP SUMMARY SHEET
Sr. No. | Manhole ITP No. | ITP DATE | Location of Works | Qty. | Type | Size | Hieght (MM) | Permit No. | Link No.
4 | 4315-035 | 2021-02-12 | Near Konark Gate To Worli Naka | 1 | FRP | 900*600 | 800 | 783247281 | MUMB0309
5 | 4315-035 | 2021-02-12 | Near Konark Gate To Worli Naka | 1 | BLOCK | 900*600 | 550 | 783247281 | MUMB0309
|  | TOTAL NO.OF MANHOLES |  | 2
Certified By
T&D JC LEAD |  | MP T&D LEAD |  | MPCM |  |  | STATE CONSTRUCTION HEAD

## Blowing Ribbon (hidden)
STERLITE TECHNOLOGIES LIMITED
ITP SUMMARY FOR BLOWING WORK
| AREA :- |  | MP 01 (MCGM)
| WO NUMBER : - |  | P11/630098168
| WO DATE : - |  | 2021-04-26
| PROFORMA INVOICE NO :- |  | TNDMNETMP01-3
| WORK PERIOD : |  | 12-02-2021 To 12-02-2021
Sr No. | ITP Date | ITP No. | Chainage |  | Manhole |  | Cable | Cable Drum No | MH Entry | MH Exit | Length | Loop Length | Total Length | Simple Plug | Link No.
|  |  | From | To | From | To | Type |  | length | length | Mtrs. | Mtrs.
1 |  |  |  |  | MH0 | MH1 |  |  |  |  | 0 | 0 | 0
2 |  |  |  |  | MH1 | MH2 |  |  |  |  | 0 | 0 | 0
3 |  |  |  |  | MH2 | MH3 |  |  |  |  | 0 | 0 | 0
4 |  |  |  |  | MH3 | MH4 |  |  |  |  | 0 | 0 | 0
5 |  |  |  |  | MH4 | MH5 |  |  |  |  | 0 | 0 | 0
6 |  |  |  |  | MH5 | MH6 |  |  |  |  | 0 | 0 | 0
[7 empty] | TOTAL 96F Ribbon | [5 empty] | 0 | 0
|  | Blowing 96 F Ribbon |  | 0
|  | Blowing 288 F Ribbon |  | 0
|  | Total Simplex Plug |  | 0

## Splicing (hidden)
| VENDOR NAME- |  | STERLITE TECHNOLOGIES LIMITED
| AREA :- |  | MP 01 (MCGM)
| WO NUMBER : - |  | P11/630098168
| WO DATE : - |  | 2020-12-19
| PROFORMA INVOICE NO :- |  | TNDMNETMP01-3
| WORK PERIOD : |  | 12-02-2021 To 12-02-2021
Sr. No. | ITP No. | ITP Date | Area Name | Link No. | SAP ID/WBS | Type of JC/FDP Use | Type of Joints | Type of OFC |  |  | No of Joints |  |  | Qty Completed | Remarks
[8 empty] | 48 | 96 | 288 | 48 | 96 | 288
1 | [13 empty] | 0
2 | [13 empty] | 0
3 | [13 empty] | 0
0
0
0
0
|  |  | TOTAL SPLICING------> |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Mat Code | MAT.DESCRIPTION |  |  |  | Qty
|  |  | 2001883667 | PANEL,DISTRIBUTION,FIBRE,12T,LT |  |  |  | 0
|  |  | 2001786731 | PANEL,DISTRIBUTION,FIBRE,16T,RIBBON |  |  |  | 0
|  |  | 2001750800 | PANEL,DISTRIBUTION,FIBRE,8T,RIBBON |  |  |  | 0
|  |  | 2001548397 | CLOSURE,JOINT,OFC,48F(6LT X 8F) |  |  |  | 0
|  |  | 2001684298 | FDP FTTX ODC 1X96 F LCAPC DUPLEX |  |  |  | 0
|  |  | 2001588170 | CLOSURE,JOINT,OFC,288F(RIBBON) |  |  |  | 0
|  |  | 2001980575 | CLOSURE,JOINT,OFC,96F(INDIVIDUAL) F/ ENTP |  |  |  | 0
|  |  | 2001575098 | CLOSURE,JOINT,OFC,96F(RIBBON) |  |  |  | 0
|  |  | 2001611527 | PANEL,DISTRIBUTION,FIBRE,96T,TYPE 4 |  |  |  | 0
|  |  | 2001611528 | PANEL,DISTRIBUTION,FIBRE,96T,TYPE 5 |  |  |  | 0
|  |  | 2001575982 | PANEL,DISTRIBUTION,FIBRE,288T,RIBBON |  |  |  | 0
| Contractor Representative |  | QSD | Site Engineer |  |  | JC Lead |  |  |  | MPCM |  |  | SCM
| Signature |  | Signature | Signature |  |  | Signature |  |  |  | Signature |  |  | Signature

## DEDUCTION (hidden)
STERLITE TECHNOLOGIES LIMITED
|  | WORK OREDER NO:- | P11/630098168
|  | PROFORMA INVOICE NO:- | TNDMNETMP01-3
Charges for Deduction due to Depth Variation as per Specifications
S. No. | Item Code | Desrciption | Length in Mtr | Rate | Amount (Rs.)
1 | NA | Normal Soil (In CuM) | #REF! | 425 | #REF!
2 | NA | Culvert/common duct/Utilityduct length deduction(mtr)-02 duct | 0 | 358 | 0
3 | NA | Culvert/common duct/Utilityduct length deduction(mtr)-03 duct | 0 | 358 | 0
4 | NA | Culvert/common duct/Utilityduct length deduction(mtr)-04 duct | 0 | 348 | 0
5 | NA | Culvert/common duct/Utilityduct length deduction(mtr)-06 duct | 0 | 347 | 0
6 | NA | Culvert/common duct/Utilityduct length deduction(mtr)-08 duct | 0 | 269 | 0
|  | Total |  |  | #REF!
|  | ROUND UP AMOUNT |  |  | #REF!
#VALUE!
| Checked By |  |  | Approved By
| QSD |  |  | CPH

## MH Deduction (hidden)
Amount To Be Debited To T & D/HDD/MT Vendors Towards In adequate Depth Block Manhole Provided as per Specification
Sr. No | PROFORMA INVOICE NO. | Vendor Name | Size of Manhole in MM | No of Manholes | Actual Depth Provide in MM | Rebate Amount per Manhole | Amount To Be recovered
1 | #REF! | STERLITE TECHNOLOGIES LIMITED | (900 X 600) | 2 | (301 To 600) | 4200 | 8400
2 | #REF! | STERLITE TECHNOLOGIES LIMITED | (900 X 600) |  | (601 To 900) | 2800 | 0
3 | #REF! | STERLITE TECHNOLOGIES LIMITED | (900 X 600) |  | (901 To 1100) | 1400 | 0
4 | #REF! | STERLITE TECHNOLOGIES LIMITED | (900 X 900) |  | (301 To 600) | 4800 | 0
5 | #REF! | STERLITE TECHNOLOGIES LIMITED | (900 X 900) |  | (601 To 900) | 3200 | 0
6 | #REF! | STERLITE TECHNOLOGIES LIMITED | (900 X 900) |  | (901 To 1100) | 1600 | 0
|  | Work Order No.- | #REF!
|  |  | TOTAL | 2 | AMOUNT TO BE DEBITED |  | 8400

## MAT CONS SHEET
MATERIAL CONSUMPTION SHEET- WORK AT MCGM AREA
PROFORMA Invoice No:- |  | TNDMNETMP01-3
WO No:- |  | P11/630098168
SERVICE PERIOD:- |  | 12-02-2021 To 12-02-2021
Area:- |  | MP 01 (MCGM)
S. No | MATERIAL CODE | MATERIAL DESCRIPTION | UOM | MUMB_0309 |  | TOTAL QUANTITY
1 | 2001957481 | DUCT,HDPE,GREY,40 ODX3.5MM T,WHITE STRPS | KM | 0.178 |  | 0.178
2 | 2001512960 | DUCT,HDPE,Red,LUB,40 OD X 3.5MM | KM | 0.178 |  | 0.178
3 | 2001512963 | DUCT,HDPE,VIOLET,LUB,40 OD X 3.5MM THK | KM |  |  | 0
| 2001980254 | OFC ARM 6LT X 2F HDPE 12F SM FRP | KM |  |  | 0
4 | 5000014404 | MANHOLE,900X600X800,BOX,MODU,FRP,HD20 | EA | 1 |  | 1
5 | 5000032778 | MANHOLE;900X600;BOX;MODU;FRP; HD20 | EA | 1 |  | 1
| 2001611527 | PANEL,DISTRIBUTION,FIBRE,96T,TYPE 4 | EA |  |  | 0
| 2001883667 | PANEL,DISTRIBUTION,FIBRE,12T,LT | EA |  |  | 0
4 | 2001602577 | SEALANT,DBC,FIBER REINFORCED,SBS 2511 | KG |  |  | 0
5 | 2001620994 | PICK,PN:RT 100/30A | EA |  |  | 0
6 | 2001805201 | HOLDER,TOOL,MICRO TRENCHING;DW:MTE-0023 | EA |  |  | 0
| 2001561088 | OFC ARM 8FX3RX4LT HDPE 96F SM FRP | KM |  |  | 0
Certified By:-
Site Engineer (STL) |  | AREA MANAGER | MPCM |  | SCH | Mat.Co-ordinator
SIGNATURE |  | SIGNATURE | SIGNATURE |  | SIGNATURE | SIGNATURE