## Sheet1
| order_type | order_no | revision_no | date | amendment of total price | previous total order price | revised/total order price | fsa_id | fsa_name | service_code | service_heading | quantity | UOM | service_rate | total_value | service_description | quantity_consume
0 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | OFC LAYING OT/HDD/MT (MCGM) | 3343435 | LAY OFC-3 DUCTS-OT-T1-CSS-96F | 552.062 | 552.062 | 505 | 278791.31 | Installation Of 3 Nos 40MM OD HDPE Ducts by Open Cut in all Types of Soil /Murrum /Hard Rock OR any other strata including Installation of MH ,DIT of 3 Ducts , 96 Blowing , FDP, Joint Closure installation,
1 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | OFC LAYING OT/HDD/MT (MCGM) | 3343459 | LAY OFC-3 DUCTS-HDD-RJIL M/C-T1-CSS-96F | 284 | 284M - Meter | 955 | 271220 | Installation Of 3 Nos 40MM OD HDPE Ducts by HDD Method in all Types of Soil /Murrum /Hard Rock OR any other strata including Installation of MH ,DIT of 3 Ducts , 96 Blowing , FDP, Joint Closure
2 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | OFC LAYING OT/HDD/MT (MCGM) | 3343442 | LAY OFC-4 DUCTS-OT-T1-CORE/AGG-96F/288F | 200 | 200M - Meter | 535 | 107000 | Preliminary route survey & Installation Of 4 Nos 40MM OD HDPE Ducts by OT Method in all Types of Soil /Murrum /Hard Soil OR any other strata including Installation of MH ,DIT of 4 Ducts , 288 & 96 F
3 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | OFC LAYING OT/HDD/MT (MCGM) | 3253116 | OPEN TRENCHG IN ALL SOIL&MURRUM-6 DUCTS | 300 | 300M - Meter | 490 | 147000 | OPEN TRENCHING IN ALL TYPES OF SOIL AND MURRUM INCLUDING
4 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | OFC LAYING OT/HDD/MT (MCGM) | 3257813 | OPEN TRENCHG IN ALL SOIL&MURRUM-8 DUCTS | 300 | 300M - Meter | 510 | 153000 | OPEN TRENCHING IN ALL TYPES OF SOIL AND MURRUM INCLUDING
5 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | OFC LAYING OT/HDD/MT (MCGM) | 3318616 | CHRG TRENC,MT,3NOS 40MM DUCT,DEPTH:450MM | 3501.658 | 3,501.658 | 476 | 1666789.21 | TRENCHING WITH THE HELP OF MICRO TRENCHING MACHINE UP TO 450 MM DEEP INCLUDING RESTORATION OF THE TRENCH AS PER THE SPECIFICATION , DEWATERING & DISPOSAL OF
6 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | OFC LAYING OT/HDD/MT (MCGM) | 3256668 | OPEN TRENCHING - 2 DUCTS | 17 | M - Meter | 460 | 7820 | CHARGES FOR OPEN TRENCHING - 2 DUCTS.
7 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | OFC LAYING OT/HDD/MT (MCGM Z-2) | 3343435 | LAY OFC-3 DUCTS-OT-T1-CSS-96F | 3500 | 3,500 | 485 | 1697500 | Installation Of 3 Nos 40MM OD HDPE Ducts by Open Cut in all Types of Soil /Murrum /Hard Rock OR any other strata including Installation of MH ,DIT of 3 Ducts , 96 Blowing , FDP, Joint Closure installation,
8 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | OFC LAYING OT/HDD/MT (MCGM Z-2) | 3343459 | LAY OFC-3 DUCTS-HDD-RJIL M/C-T1-CSS-96F | 470.165 | 470.165 M | 825 | 387886.13 | Installation Of 3 Nos 40MM OD HDPE Ducts by HDD Method in all Types of Soil /Murrum /Hard Rock OR any other strata including Installation of MH ,DIT of 3 Ducts , 96 Blowing , FDP, Joint Closure
9 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | OFC LAYING OT/HDD/MT (MCGM Z-2) | 3343442 | LAY OFC-4 DUCTS-OT-T1-CORE/AGG-96F/288F | 1670 | 1,670 | 510 | 851700 | Preliminary route survey & Installation Of 4 Nos 40MM OD HDPE Ducts by OT Method in all Types of Soil /Murrum /Hard Soil OR any other strata including Installation of MH ,DIT of 4 Ducts , 288 & 96 F
10 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | OFC LAYING OT/HDD/MT (MCGM Z-2) | 3253116 | OPEN TRENCHG IN ALL SOIL&MURRUM-6 DUCTS | 127 | 127M - Meter | 466 | 59182 | OPEN TRENCHING IN ALL TYPES OF SOIL AND MURRUM INCLUDING
11 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | OFC LAYING OT/HDD/MT (MCGM Z-2) | 3318616 | CHRG TRENC,MT,3NOS 40MM DUCT,DEPTH:450MM | 2760 | 2,760 | 442 | 1219920 | TRENCHING WITH THE HELP OF MICRO TRENCHING MACHINE UP TO 450 MM DEEP INCLUDING RESTORATION OF THE TRENCH AS PER THE SPECIFICATION , DEWATERING & DISPOSAL OF
12 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | BLOWING & SPLICING | 3252601 | SPLICING,JOINTING & TERMINATION-48F | 720 | 720.000 NOS - No. | 112 | 80640 | CHARGES FOR SPLICING,JOINTING & TERMINATION OF 48F FIBRE.
13 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | BLOWING & SPLICING | 3252602 | SPLICING,JOINTING & TERMINATION-96F | 2688 | 2,688.000 | 112 | 301056 | CHARGES FOR SPLICING,JOINTING & TERMINATION OF 96F FIBRE.
14 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | BLOWING & SPLICING | 3252603 | SPLICING,JOINTING & TERMINATION-288F | 4100 | 4,100.000 | 112 | 459200 | CHARGES FOR SPLICING,JOINTING & TERMINATION OF 288F FIBRE.
15 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | BLOWING & SPLICING | 3252598 | BLOWING OF 48F | 20962 | 20,962 | 10 | 209620 | CHARGES FOR BLOWING OF 48F FIBRE.
16 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | BLOWING & SPLICING | 3252599 | BLOWING OF 96F | 10448 | 10,448 | 15 | 156720 | CHARGES FOR BLOWING OF 96F FIBRE.
17 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | BLOWING & SPLICING | 3252600 | BLOWING OF 288F | 4399 | 4,399 | 25 | 109975 | CHARGES FOR BLOWING OF 288F FIBRE.
18 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | ROW MCGM | 3251505 | CHARGES FOR DOCUMENT PROCESSING | 33279.15 | 33,279.150 | 260 | 8652579 | CHARGES FOR OBTAING ROW PERMISSION AND NOC / BG RELEASE
19 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | CHARGS INST FRP MH/HH - 900x600 | 3235737 | FRP MANHOLE INSTALLATION | 183 | 183.000 | 4365 | 798795 | MH installations works including, but not limited to, taking over all##OWNER supplied free issue materials from designated place of issue,##transportation to the contractor's warehouse/ site for
20 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | CHARGS INST FRP MH/HH - 900x900 | 3235737 | FRP MANHOLE INSTALLATION | 45 | 45.000 | 4365 | 196425 | MH installations works including, but not limited to, taking over all##OWNER supplied free issue materials from designated place of issue,##transportation to the contractor's warehouse/ site for
21 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | S& I OF MANHOLE (BLOCK MH 600*900) | 3253157 | SUPPLY & INSTALLATION OF MANHOLE | 140 | AU - Activity unit | 15423 | 2159220 | CHARGES FOR SUPPLY & INSTALLATION OF MANHOLE.
22 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | S& I OF MANHOLE (BLOCK MH 900*900) | 3253157 | SUPPLY & INSTALLATION OF MANHOLE | 130 | AU - Activity unit | 17460 | 2269800 | CHARGES FOR SUPPLY & INSTALLATION OF MANHOLE.
23 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | S& I OF MANHOLE (BLOCK MH 800*1200) | 3253157 | SUPPLY & INSTALLATION OF MANHOLE | 90 | AU - Activity unit | 14550 | 1309500 | CHARGES FOR SUPPLY & INSTALLATION OF MANHOLE.
24 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | DWC PIPE | 3318198 | S&I DBL WALL CORRUGATED DUCT-110NB | 8500 | 8,500 | 116 | 986000 | CHARGES FOR SUPPLY AND INSTALLATION OF DOUBLE WALL CORRUGATED (DWC) DUCTS - 110 NB
25 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | DIT | 3250482 | CHRGS:DUCT INTEGRITY TEST | 40407 | 40,407 | 3 | 121221 | CHARGES FOR DUCT INTEGRITY TEST(DIT).
26 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | OFC LAYING OT/HDD/MT - NON-MCGM | 3318616 | CHRG TRENC,MT,3NOS 40MM DUCT,DEPTH:450MM | 572 | 572M - Meter | 408 | 233376 | TRENCHING WITH THE HELP OF MICRO TRENCHING MACHINE UP TO 450 MM DEEP INCLUDING RESTORATION OF THE TRENCH AS PER THE SPECIFICATION , DEWATERING & DISPOSAL OF
27 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | OFC LAYING OT/HDD/MT - NON-MCGM | 3343435 | LAY OFC-3 DUCTS-OT-T1-CSS-96F | 11830 | 11,830 | 425 | 5027750 | Installation Of 3 Nos 40MM OD HDPE Ducts by Open Cut in all Types of Soil /Murrum /Hard Rock OR any other strata including Installation of MH ,DIT of 3 Ducts , 96 Blowing , FDP, Joint Closure installation,
28 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | OFC LAYING OT/HDD/MT - NON-MCGM | 3343459 | LAY OFC-3 DUCTS-HDD-RJIL M/C-T1-CSS-96F | 13469 | 13,469 M - Meter | 705 | 9495645 | Installation Of 3 Nos 40MM OD HDPE Ducts by HDD Method in all Types of Soil /Murrum /Hard Rock OR any other strata including Installation of MH ,DIT of 3 Ducts , 96 Blowing , FDP, Joint Closure
29 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | PCC MCGM | 3143695 | PROV &LAYING PCC M:15-ALL THK | 11.045 | 11.045 | 4656 | 51425.52 | PROV &LAYING PCC M:15-ALL THK.
30 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | PCC NON-MCGM | 3143695 | PROV &LAYING PCC M:15-ALL THK | 124.665 | 124.665 | 3880 | 483700.2 | PROV &LAYING PCC M:15-ALL THK.
31 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | NON FIM Material(OFC/BOI/) | 3242510 | PROVIDING OF END PLUG | 1721 | 1,721.000 | 44 | 75724 | Providing of End Plug
32 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | NON FIM Material(OFC/BOI/) | 3319693 | S&I COUPLER,F/40MM HDPE DUCT | 25 | EA - each | 120 | 3000 | CHARGES FOR SUPPLYING AND FIXING OF COUPLER FOR 40 MM HDPE DUCT#
33 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | NON FIM Material(OFC/BOI/) | 3318198 | S&I DBL WALL CORRUGATED DUCT-110NB | 172 | 172M - Meter | 116 | 19952 | CHARGES FOR SUPPLY AND INSTALLATION OF DOUBLE WALL CORRUGATED (DWC) DUCTS - 110 NB
34 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | NON FIM Material(OFC/BOI/) | 3319692 | S&I SIMPLEX PLUG,F/40MM HDPE DUCT | 468 | EA - each | 49 | 22932 | CHARGES FOR SUPPLYING AND FIXING OF SIMPLEX PLUG FOR 40 MM HDPE DUCT#
35 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | NON FIM Material(OFC/BOI/) | 3086352 | E301-LAYING OF WARNING TAPE | 13900.5 | 13,900.500 | 6 | 83403 | 60
36 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | NON FIM Material(OFC/BOI/) | 3294582 | L/C FOR INSTL GI PIPE 110NB;MEDIUM CLASS | 157 | 157M - Meter | 765 | 120105 | LABOUR CHARGES FOR INSTALLATION OF MEDIUM CLASS 110 NB GI PIPES CONFORMING TO IS 1239 (PART - I) 2004 (REVISED UP TO DATE) & IS
37 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | NON FIM Material(OFC/BOI/) | 3245488 | P&L 50 MM GI PIPE | 16 | M - Meter | 325 | 5200 | Providing & Laying 50mm dia B Class GI pipe (Tata/ Jindal /Asian or
38 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | ROW NON MCGM (MP-09) | 3251505 | CHARGES FOR DOCUMENT PROCESSING | 18308 | 18,308 M - Meter | 160 | 2929280 | CHARGES FOR OBTAING ROW PERMISSION AND NOC / BG RELEASE
39 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | P&F SAFETY BARRIER | 3347603 | P&F SAFETY BARRIER DURING OSP WORKS | 18784 | 18,784 M - Meter | 28 | 525952 | Providing and Installing Safety Barricades, Arranging traffic control marshals, Mahanet specific printing, LOGO and Symbols as per specifications provided by MCGM etc.
40 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | VERTICAL BLOWING | 3293219 | VERTI.BLOWING OF 288F OFC-OUTDOOR INSTLN | 24 | 24 M - Meter | 55 | 1320 | Providing and Installing Safety Barricades, Arranging traffic control marshals, Mahanet specific printing, LOGO and Symbols as per specifications provided by MCGM etc.
41 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | S&I PERFORATED TYPE CABLE TRAY 200X50MM | 3251951 | S&I PERFORATED TYPE CABLE TRAY | 10 | M - Meter | 520 | 5200 | SUPPLY AND INSTALLATION OF PERFORATED TYPE CABLE TRAY NEATLY ALONG THE##AGREED ROUTE WHEREVER REQUIRED. PROPER UTILISATION OF TEES, BENDS &##CROSS AS
42 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | INSTALLTION PERFORATED TYPE CABLE TRAY 2 | 3306814 | S & I OF CBL TRAY COVER,200MM | 10 | M - Meter | 194 | 1940 | Installation in horizontal & vertical formation of GI prefabricatedladder type/perforated galvanized steel sheet cable trays cover,of different widths and delivered in standard lengths along with Coupler plates and
43 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | CHRG MT- RSTRTN W/5.65% BT CC SEAL COAT | 3346367 | CHRG MT- RSTRTN W/5.65% BT CC SEAL COAT | 4065 | 4,065 | 325 | 1321125 | Excavation in trench/road . Providing and laying hot mixed premix seal coat with 5.65% of VG-30 bitumen by weight of mix bitumen content including rolling by 8-10T vibratory roller etc complete as directed by EIC
44 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | CHRG MT- RSTRTN W/5.65% BT CC SEAL COAT | 3345959 | CHRG F/MT RSTRTN W/2000MM WDTH PAVER BLK | 616.9 | 616.900 M2 - Square meter | 750 | 462675 | Excavation in trench##P/L Sand metal layer ( 5 layers of 75mm each). Providing, laying, spreading & compacting specified crushed stone in granular sub-base course including premixing the material in uniform
45 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | SUE SERVICES (MT) | 3238951 | SUE SERVICES | 5911 | 5,911 | 28 | 165508 | Excavation in trench##P/L Sand metal layer ( 5 layers of 75mm each). Providing, laying, spreading & compacting specified crushed stone in granular sub-base course including premixing the material in uniform
46 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | SUE SERVICES (HDD) | 3238951 | SUE SERVICES | 13469 | 13,469 | 28 | 377132 | 1
47 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | NOC-BG MP03 | 3346243 | CHRG F/MCGM AREA NOC AND BG RELEASE | 5921 | 5,921 | 190 | 1124990 | Project Management Charges for submission of proper documents to authorities for obtaining necessary NOC for RI works and obtaining approval for release of BG submitted by RJIL
48 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | SRPF POI site & 2 ENB COW sites (MP03) | 3251505 | CHARGES FOR DOCUMENT PROCESSING | 1 | M - Meter | 201537 | 201537 | CHARGES FOR OBTAING ROW PERMISSION AND NOC / BG RELEASE
49 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | Road Crossing Above 10 Mtr | 3107471 | MISCELLANEOUS WORK | 1 | 1.000 | 9200 | 9200 | CHARGES FOR OBTAING ROW PERMISSION AND NOC / BG RELEASE
50 | WORK CHANGE ORDER | 630125209 | 0011 | 28.02.2022 | 1.30- | 55999298.31 | 55999297.01 |  | Road Crossing below 10 Mtr | 3107471 | MISCELLANEOUS WORK | 7 | 7.000 | 7200 | 50400 | ___________________________________________________________________________________________________